## V and V
Sub System | Sub - System element | Associated Requirement | Validation steps | Success Statement' | Verification Steps | Verification description
Control | Implementing Translation transform | To move DDR robot in straight line | the wheels pi and arduino executing this operation and gauge uncertainty | The robot reliably moves in a straight line on relatively flat surfaces | To take a manually generated dataset for a scan path with multiple straight and roational segments and travel this path
| Implementing rotation transform | To implement DDR turning of the robot on a point | pi and arduino executing this operation and gauge uncertainty | The robot can pivot with predicatable error to a target no of degrees
| Enable subsystem | Sending signal that switches state to operation of subsystems | Use the pi to demonstrate states of the arduino by actuating parts | The motion state of the robot can be controlled (straight line/ turn)
| Communicating encoder data to pi | Sending data that is effectively unpacked by the raspberry | To arduino print encoder position and print the same data in python | The angular position of the wheels can be used for logic
Computation | Navigation Location Checking | Characterise accurate position estiate is at any given time | To specify a position co ordinated by hand and prove the robots knowledge of achieving this position | the robot knows where on the green it is to a tolerance | To take the scan path identify a target object on this path and deviate the path such that the tool is aligned to a known uncertainty
| Vector Calculation | Need for a numerical representation of location data | to specify a destination and get the robot to express the vector to it | The robot can perform directional computation
| Route Planning | need for a method to create paths and adjust them for pitchmarks | Have the robot deviate its path to a point specified after its journey begins and check numerically represent process reliability | The robot can perform its own navigation
API Formating
| Object detection | Identify pitch marks and ground information | Take the robot to a pitchmark and identify it with specified confidence | The robot can identify pitchmarks and hazards
Repair | Entering pitch repair state | Need to minimise overworking raspberry and arduino, seperating tasks | Trigger a state machine that stops everything and actuated correct components | The robot knows when to perform pitch repair operations | The robot can be placed in proximity of a pitch mark identify it insert the tool around the mark and log the success
| Instertion and removal from ground | Not break, raise ground, allow for long term healing | Prove the stepper can deliver torque to insert and remove spikes | the robot can penetrate ground
| Repeat motion and rotate reliably | To pentrate the outside of the pitch | Measure the servo rotation with consistent linear motion | The robot can penetrate around a pitch mark
| Camera success evaluation | Need to log effectiveness and alert greenkeeper of repair quality | After functionality achieved derivation of a metric for success | The robot knows if It has succceeded or not
Probe | Entering probe state | Need to minimise overworking raspberry and arduino, seperating tasks | Trigger a state machine that stops everything and actuated correct components | The robot knows when to probe | While travelling a path the robot can be interupted at a pre planned time and perform the probe such that the data can be presented on the app
| Insertion and removal | Need to penetrate ground for test | Prove the stepper can deliver torque to insert and remove spikes | The probe can penetrate ground
| Arduino Reading data | Need to decode rs485 protocol | To check soil levels and characterise error in probe reading | The soil data is accurate
| Sending Data to raspberry | To get the data to the point it can be processed | Take a reading from probe and transfer it so it can be printed in python | The soil data is available for computation
| Probe data processing | To get data such that it is useful to greenkeepers | Derive a algorith to evaluate green health | The soil data is useful to the greenkeeper
Cloud APIs | Data format |  |  |  | Repair success, Green health metrics and robot location can be presented to the home screen
Updatign JSON
Front end App | Present robot data as described | Greenkeeper useability | Show on app screen | The app is interacting with the greenkeeper
| Send instructions | So greenkeeper can exert control of robot | Triggering a state from app to pi to arduino | The greenkeeper is working with th robot
Aknowledge of robot update

## Gantt
# | Task Name + Members Responsible | Date
1 | Top Level System Design | Semester 1
| Members Responsible : All | Week 6
2 | Wheel, Motor and Motor Controller Selection | Semester 1
| Members Responsible : Amir, Blair and Jake | Week 7-9
3 | Application UI + Functionality Design | Semester 1
| Members Responsible : Jack and Job | Week 7
4 | Soil Research + Probe Tool Component Selection | Semester 1
| Members Responsible : Job and Amir | Week 8
5 | Design Decision sheet | Semester 1
| Members responsible | Week 7-9
6 | Initial Repair Tool Design + Testing | Semester 1
| Members Responsible : Jake and Blair | Week 8
7 | Redesigned Repair Tool | Semester 1
| Members Responsible : Amir, Blair and Jake | Weeks 9 - 10
8 | Finalisation of Component Selection | Semester 1
| Members Responsible : Amir, Blair and Jake | Week 9
9 | AWS Integrated Deployment | Semester 1
| Members Responsible : Jack | Week 8
10 | Next JS Application Development | Semester 1
| Members Responsible : Jack and Job | Weeks 8 - 9
11 | API Development for Robot-App Communication | Semester 1
| Members Responsible : Jack and Job | Weeks 10 - 11
12 | Pitch mark Object Detection Model Creation | Semester 1
| Members Responsible : Jack and Job | Weeks 10 - 12
13 | Raspberry Pi Connection with Application | Semester 1
| Members Responsible : Jack and Blair | Week 11
14 | Verification and validation excerise | Semester 1
| Members Responsible : Jack and Blair | Week 11
15 | Technical risk matrix | Semester 1
| Members Responsible | Week 11
16 | Robot Skeleton and Shell CAD Design | Semester 1
| Members Responsible : Amir Blair and Jake | Week 11
17 | Interim Report Work + Diagram Creation | Semester 1
| Members Responsible : All | Week 11
18 | Assembly of Robot | Semester 1
| (Note this is done in spare time over the Christmas break) | Week 12 –
| Members Responsible : Amir Blair and Jake | Semester 2
Week 0
19 | Arduino sketch for DDR and encoders | Semester 2
| Member responsible: | Week 0
20 | Arduino sketch for rs485 | Semester 2
| Member responsible: | Week 0
21 | Arduino sketch for rotating tool | Semester 2
| Member responsible: | Week 0
22 | Arduino maincode for moving through states: | Semester 2
| Member responsible: | Week 0
23 | Arduino code for packing and sending feedback data | Semester 2
| Members responsible: | Week 0
24 | GNSS Navigation Coordinate Fetching to Pi | Semester 1
| (Note this is done in spare time over the Christmas break) | Week 12 –
| Members Responsible : Jack | Semester 2
Week 0
25 | Grass Health – Decision Tree Development for Grass Health | Semester 1
| (Note this is done in spare time over the Christmas break) | Week 12 –
| Members Responsible : Job | Semester 2
Week 0
26 | Object Detection- Conversion of Detected Object to Coordinate to Repair | Semester 2
| Members Responsible : Jack and Jake | Weeks 1-2
27 | Object Detection – Model to detect successful and unsuccessful repairs | Semester 2
| Members Responsible : Job | Week
28 | Movement – Conversion of next point to a movement vector with compass input | Semester 2
| Members Responsible : Job | Week
29 | Movement – Differential Drive Transform and Odometry | Semester 2
| Members Responsible : Job | Week
30 | Movement – Calibration of Motors to Turn ‘X’ degrees | Semester 2
| Members Responsible : Job | Week
31 | Movement – Calibration of Motors to Move Straight for ‘X’ meters | Semester 2
| Members Responsible : Job | Week
32 | Movement - Calibration of rack an pinion for both subsystems | Semester 2
| Members responsible | Week
33 | Development - Plan + document for on green testing - Navigation | Semester 2
| Members responsible | Week
34 | Development - Plan + document for on green testing - Subsystems | Semester 2
| Members responsible | Week
35 | Development - Plan + document for on green testing - Navigation + subsystems | Semester 2
| Members responsible | Week
36 | Grass Heath – App Design to display probe information | Semester 2
| Members Responsible : Job | Week
37 | Repair Tool – Calibration of Tool for Optimal Repair | Semester 2
| Members Responsible : Job | Week
38 | Raspberry Pi – Code to Control Scanning Green | Semester 2
| Members Responsible : Job | Week
39 | Raspberry Pi – Code to Deploy Repair and Update App | Semester 2
| Members Responsible : Job | Week
40 | Raspberry Pi – Main Dispatcher and Thread Manager Code | Semester 2
| Members Responsible : Job | Week
41 | On Green Testing | Semester 2
| Members Responsible : Job | Week
42 | API Request Reduction Improvements | Semester 2
| Members Responsible : Job | Week
43 | Final Report Work | Semester 2
| Members Responsible : Job | Week
44 | Demonstration Work | Semester 2
| Members Responsible : Job | Week

## Risk matrix
No. | Risk | Severity | Likelihood | Score | Mitigation
1 | Navigation unable to determine location | 5 | 3 | 15 | Use of GNSS + RTK + Encoders + Feedback logic
2 | Repair tool mechanical failure (detail different types + stuck in ground) | 2 | 3 | 6 | Mechnaincal components for this are low cost + available
3 | API request limits | 2 | 5 | 10 | Assimilate API requests + lower request rate
4 | Wheels mobility issues, large wheel size translation resolution too high issues | 4 | 1 | 4 | Use cheap hobbyist wheels descopes the robot from being a commercial platform
5 | Wheel motors – inrush current | 5 | 2 | 10 | Components slected with protection and high max ratings use of a fuse mitigates this
6 | Raspberry pi RAM limit | 3 | 1 | 3
7 | Concurrency issue with PI multi threading (i.e. need tasks to run concurrently) | 2 | 2 | 4 | Python threading library + thread management system
8 | Current regulation (for all components) | 5 | 1 | 5 | UPS power has internal protection to overload
9 | Battery life | 2 | 2 | 4 | 7800 mAh on UPS + can use a secondary power system (18650 batteries)
10 | Robot stuck in scan path (arbitrary) | 1 | 5 | 5 | Alert greenkeeper
11 | Poor translation resolution of gear teeth /mechanisms | 2 | 3 | 6 | New gears and racks would be required
12 | Cloud deployment down | 4 | 1 | 4 | Amazon wont let their server go down for long periods
13 | Stepper torque being too low to penetrate ground | 4 | 3 | 12 | buy new motors / linear actuator
14 | Resistance from ground causing stepper current to spike | 3 | 1 | 3 | Use a fuse/ test with ammeter
15 | Water getting into DC motors | 4 | 2 | 8 | Only use in acceptable conditions
16 | Raspberry pi motor controller receiving overload | 5 | 2 | 10 | Test exclusively with a fuse between controller and pi before mounting
17 | Lack of control on motor current transient | 4 | 2 | 8 | Test and use a ramp/ steps type function controlling wheels
18 | Lack of control of inertial forces | 3 | 4 | 12 | Use ramp/ step functions on motors + calibrate steering
19 | Uncertainty in rotation/ distance building such that robot gets lost | 4 | 3 | 12 | Using feedback from wheel encoders to validate location and bearing estimates
20 | Not being able to use a green of sufficient quality | 5 | 2 | 10 | Perform navigation of grass turf and recreate turf for repair
21 | Not enough flattening of the / lack of reaction force – low risk/ roots are still healed | 1 | 4 | 4 | Turf still healed golfers will need to flatten the partial repair
22 | Difference in frictional torque in each wheel motor – steering could be affected | 3 | 1 | 3 | Switch to two wheels differential drive - descopes project